## Detail & Big Picture
ROI Range Categories & Logic
[5 empty] | 273309 | ROI Label | Description | Financial Impact Range (12-month) | Combined for Data Validation
[5 empty] | 546618 | No Financial Impact | Aesthetic or exploratory; no measurable return | $0 | No Financial Impact ($0)
[6 empty] | Minimal Return | Marginal efficiency or UX improvement | $25k–$75k | Minimal Return ($25k–$75k)
[6 empty] | Low ROI | Small operational or retention gain | $75k–$200k | Low ROI ($75k–$200k)
[6 empty] | Moderate ROI | Noticeable cost savings, productivity lift, or service improvement | $200k–$500k | Moderate ROI ($200k–$500k)
[6 empty] | High ROI | Directly improves revenue, utilization, or throughput | $500k–$1.5M | High ROI ($500k–$1.5M)
[6 empty] | Strategic ROI | Enables sustained growth, market positioning, or customer expansion | $1.5M–$3M | Strategic ROI ($1.5M–$3M)
[6 empty] | Transformational ROI | Unlocks new revenue streams or major OPEX reductions | $3M–$6M | Transformational ROI ($3M–$6M)
[6 empty] | Enterprise-Level ROI | Critical to business continuity, automation, or brand turnaround | $6M–$12M | Enterprise-Level ROI ($6M–$12M)
[6 empty] | Game-Changer ROI | Rewrites the business model or competitive position | >$12M | Game-Changer ROI (>$12M)
Initiative Summary
In/out of Scope | High Level Deliverable | Detail | Business Benefit Type | ROI Narrative | Feature Points Total
In Scope | Girbau Sapphire Connection | Create data pipeline between Continental washers and applicaiton using the Girbau Sapphie Connection | AI Optimization, Equipment OEE , Preventative Maintenance |  | 1.9
In Scope | iConnect Connection | Create data pipeline between Union Dry Cleaners and application using the iConnect pathway | AI Optimization, Equipment OEE , Preventative Maintenance |  | 1.3
In Scope | Dryer Intelligence | Configure an IOT solution using off-the-shelf hardare to monitor dryer performance, then link performance to application. analytics, AI insights, capital management. Inclusive of technology and infrastructure development, hardware definition, alerting thresholds, and notification. Learnings from configuration and development of pipelines will create synergies in enabling similar capability to washers and drycleaners | AI Optimization, Equipment OEE , Preventative Maintenance, Garment Cost of Quality | As drying time increases, 1. risk of overdrying increases leading to increase in garment shrink (### impact over last 12 months) 2. Volume of garments dried capacity decreases leading to an increase in machines needed. (Example: If drying time on average is 14 min in excess, overall requirement for machines in increased at $XXX per machine) | 7.4
In Scope | Washer Intelligence | IoT, existing equip database configuration, analytics, AI insights, capital management | AI Optimization, Equipment OEE , Preventative Maintenance, Garment Cost of Quality |  | 0
In Scope | Dry Cleaner Intelligence | IoT, existing equip database configuration, analytics, AI insights, capital management | AI Optimization, Equipment OEE , Preventative Maintenance |  | 0.5
In Scope | Plant Floor Digital Twin | Transformation of data from all sensors into intelligent statuses displayed on a representative digital floor for quick decision making | Communication, AI Optimization, Preventative Maintenance |  | 3.1
In Scope | Asset Utilization Optimization & Preventative Maintenance | Single source of truth for machine operation parameters, trends, and analytics driving enhanced issue resolution | AI Optimization, Equipment OEE , Increased Processing Volume, Preventative Maintenance |  | 0.4
In Scope | Equipment Alerts & Maintenance Action Tracking & Management | AI and machine learning categorization of equipment operating trends with defined thresholds. When threshhold or trend detects anomalies, tickets are created to take action. | Preventative Maintenance, Communication, Increased Processing Volume, Equipment OEE |  | 0
In Scope | Asset Management & Capacity Forecasting | Dashboard communicating overall asset utilization, status, downtime event history, and MTTR | Communication, Operating Costs Reduction, Equipment OEE , Increased Processing Volume |  | 0.8
In Scope | Capital Deployment Optimization & Forecasting | View tracking asset information, cost (replacement cost & salvage value), age, replacement priority, and estimation of remaining life | AI Optimization, Capital Expenditures Forecasting, Equipment OEE |  | 4
In Scope | Holistic Preventative Maintenance Tracking System | View and action upon outstanding tickets, time and cost of repairs, maintenance history, and recommend/schedule preventative maintenance activities. Update: Rent the Runway chose to use MaintainX to handle mainenance ticketing, parts management, and other maintenance actions. ClearObject will continue with the delivery of much of the proposed application's features, less maintenance features, and add a connection into MaintainX's platform. | AI Optimization, Equipment OEE , Preventative Maintenance, Operating Costs Reduction |  | 0.9
Out of Scope | Customer Sentiment Digital Twin | Aggregation of customer sentiment from social media. Single source for content referencing Rent the Runway, calculate NPS (current & trending), detractors, and enables swift action for repair. Relate timeperiod of posts to equipment actions with drilldown on root cause and preventative actions | Customer Success, Garment Cost of Quality |  | 2.3
In Scope | Soap Dosing Reliability | IoT solution to improve reliability of solvent dosing pumps. System to assure operations the proper amount of solvent was actually delivered to the machine. Will create connection to existing Brightwell dosing pumps, create a data pipeline to cloud service, for ingestion and analysis within our applicaiton. | Garment Cost of Quality, Equipment OEE , Preventative Maintenance |  | 1.4
Out of Scope | Quality Inspection Throughput | A measure of volume of garments per hour by operators at manual quality inspection stations. Anomolies may lead to quality defects and misses | Garment Cost of Quality, Increased Processing Volume, Customer Success |  | 0.7
In Scope | Conversational AI Performance Interrogator | Integration of a conversational AI to parse questions and prompts, then return data driven insights and results on plant performance. | AI Optimization, Communication |  | 1.6
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Rent the Runway Instructions,
Review “Features” tab & validate
  Assumptions,
  Implementation plan,
  Priority
On “Detail & Big Picture” tab, Initiative Summary captures overall ROI & level of effort (Feature Points) associated with each initiative.
Data will be displayed showcasing optimal prioritization.

## Features
Initiative Category | High Level Deliverable | Feature Name | Description | ROI Logic | Priority | Feature Points
Existing System Integration/Connectivity | Girbau Sapphire Connection | API/other connection to Girbau Sapphire | Develop a connection strategy to extract data from the Girbau Sapphire system for placement within Rent the Runway's Google Cloud databases. This will provide data accessiblity to the Continental wet washing and Continental drying machines to be able to capture measurements gathered by the Girbau Sapphire software. Task is challenging due to no documentation on API connectivity from Girbau - likely due to the value proposition for their service is built upon the analytics within their proprietary software. Connection may involve discussions with Girbau engineering and sales to negotiate a path forward. |  |  | 1.9
Existing System Integration/Connectivity | iConnect Connection | Network monitoring connection into iConnect | Develop a connection strategy to extract data from the iConnect system for placement within Rent the Runway's Google Cloud databases. This will provide data accessiblity to the Union dry cleaning machines. Investigation is needed to determine connection strategy, as there is no data storage within the iConnect system and can only be remotely accessed for viewing of current operating conditions. |  |  | 1.3
IoT Sensing | Dryer Intelligence | IoT Sensor Strategy for Dryers (MVP Deployment to 10 Dryers) | Define the business requirements for hardware to be installed onto dryers for selection of appropriate IoT base station, nodes, and sensing modules to capture needed data. These devices to be designed with low-power electronics, efficient heat dissipation, current limiting, and galvanic isolation for fault protection. Components must be rated for the specific hazardous zone where they will operate (explosion-proof/ hazardous environment compliance where applicable). The specific use cases considered for this deployment include, 1. Measurement of temperature/humidity within the dryer exhaust vent to deliver a high confidence in the temperature/humidity within the dryer as a means of determining garment dryness level and cycle completion timeliness. 2. Measurement of airflow within the dryer exhaust vent to predict operational/maintenance needs (e.g. filter cleaning or downstream blockages). A trend on airflow will enable predictive maintenance and action forecasting. 3. Measurement of machine vibration. Through monitoring micro-vibrations of the machine throughout cycles, intelligence is enabled on the machine for enhanced actioning and decision making. This includes machine utilization, predictive maintenance, development of trendlines for healthy operations to identify events needing attention. Scope, 1. Define business requirements for the hardware and hardware procurement. 2. Purchase of 10 sensor kits. Kit will include the IoT device (gateway/router/edge device) and the sensors. 3. Hardware/sensor configuration 4. Installation coordination 5. Development of the data pipelines and storage systems. 6. Testing of production solution Feature points = 1.8 (for dev) + 0.8 (for hardware) | Garment Shrinkage: A highcost of non-quality and machine-related garment defects is garment shrink. Overdrying garments is a key contributor leading to garment shrinkage due to high risk of over-drying. By intelligently monitoring garment dryness level, we can minitgate garment shrinkage by preventing overdrying. By reducing the probability of a defect (shrinkage) in a garment, garment expected life is increased, thereby leading to lower inventory requirements and replacement costs. Preventative Maintenance: Improved asset longevity, maintenance forecasting, and lower energy consumption when machine is operating in as-designed condition. Asset Utilization: By avoiding the common event of over-drying which leads to increased operating time for a single load, the plant drying capacity is increased. With increased capacity through efficiently utilizing existing equipment, capital requirements for the procurement of additional machines is reduced. |  | 2.6
IoT Sensing | Dryer Intelligence | IoT Sensor Strategy for Dryers (Phase 2 Deployment to Remaining 21 Dryers) | Procurement and configuration of 25 more IoT devices for dryers to be installed at EWR for remaining 21 dryers (+4 spares) Feature points 1 (for dev) + 1.9 (for hardware) |  |  | 2.9
Shop Visuals | Dryer Intelligence | Dryer Looker dashboard | Development of a looker dashboard to display analytics, trends, and alert thresholds of the installed dryer IoT sensors. Looker dashboard to be connected to the enterprise data systems in Google Cloud. Primary function of the looker dashboard is to deliver operational insights on machine performance directly to the machine operators and technicians. Will need to procure a monitor or screen for installation or repurposing to place at dryer station. Looker dashboard to be developed specifically for operator feedback and machine monitoring. |  |  | 0.2
Existing System Integration/Connectivity | Dry Cleaner Intelligence | Dry Cleaner: PLC Data Integration (Columbia) | Tap into and pull data from the existing PLC on the "Columbia TL HCS 800 N2" dry cleaning machines. This integration will need to be custom developed and configured with RtR IT and engineering, as not all equipment has operational connections for data extraction. | Leverages existing, on-machine data (if available) to integrate into the Digital Twin with minimal hardware cost |  | 0.5
Digital Twin & Operational Insights | Dryer Intelligence | Dryer MVP: GCP Data Pipeline | Production-grade data ingestion pipeline into GCP (via Pub/Sub or MQTT) for the dryer sensing systems. | Creates a scalable foundation for all future IoT data, ensuring system is future-proof. |  | 0.2
Digital Twin & Operational Insights | Dryer Intelligence | MQTT Broker & Alerting Setup | Develop the foundations in the cloud (MQTT broker setup,pattern for pipeline from MQTT to BQ, and a baseline alerting service) to enable secure connection and communication between the IoT base station and the RtR cloud service. |  |  | 0.3
Digital Twin & Operational Insights | Dryer Intelligence | Dryer MVP: Cycle Completion Monitoring | Backend service and model to detect complete vs. incomplete dryer cycles. | Reduces garment rework and minimizes quality escapes by ensuring cycles are completed correctly. |  | 0.2
Digital Twin & Operational Insights | Dryer Intelligence | Dryer MVP: Automated Alerts | Automated alerts via Email, SMS, or push when anomalies (e.g., incomplete cycle, high temp) are detected. | Delivers immediate, actionable insights to operators to prevent or address issues in real-time. |  | 1
Digital Twin & Operational Insights | Plant Floor Digital Twin | Factory Layout Dashboard | The main /dashboard page. Develop an interactive SVG or canvas web view of the NJ facility layout. This view must be a digital representation of the factory floor, showing all zones (Inbound, Tagging, Wet Cleaning, etc.) . Requires a base facility map asset. Dashboard to ingest sensor and API data from equipment and align to a status, which will be colorized on the dashboard for quick issue identification and drill down. | Provides a single source of truth for plant health; institutionalizes lean visual management. |  | 0.7
Digital Twin & Operational Insights | Plant Floor Digital Twin | Real-Time Machine Tile Status | Each machine on the factory layout must be a "tile" that ingests data from IoT sensors. The tile must change color (e.g., Green, Orange, Red) based on its current state (OK, Warning, Down). Must include tooltips that show key metrics on hover. | Reduces problem detection time from weeks to hours. Delivers a concise, holistic view of plant operations at a glance |  | 1.2
Digital Twin & Operational Insights | Plant Floor Digital Twin | Machine Detail Modal | A pop-up modal or dedicated page (/machines/[id]) triggered by clicking a machine tile. This view must display detailed metrics, health trends (see DT-05), maintenance history, and the last alerts for that specific asset. | Shortens decision latency from floor to leadership by providing immediate drill-down data for root cause analysis |  | 0.2
| Plant Floor Digital Twin | Dashboard Filtering & Search | A UI component to filter the factory layout view. Must support filtering by equipment type (Washer, Dryer, etc.), status (Warning, Down), and zone. Must include initial filter types: View All, Dryers, Dry Cleaners, Washing Machines, Soaping Pumps, and Line/Conveyor Operations . | Allows operators and managers to reduce noise and focus on specific asset types or problem areas, speeding up diagnostics. |  | 0.2
Digital Twin & Operational Insights | Asset Utilization Optimization & Preventative Maintenance | Anomaly Detection (Prototype) | An AI routine (prototype) to classify live sensor readings against a baseline profile to flag outliers. | Proactively identifies machine health issues before they cause downtime or garment defects. |  | 0.4
Digital Twin & Operational Insights | Equipment Alerts & Maintnenance Action Tracking & Management | 1-Click Ticket Creation | A button on an alert or machine modal to "Create Maintenance Ticket" that pre-fills asset info. | Closes the loop between problem detection and resolution, reducing administrative friction. |  | 0.8
Digital Twin & Operational Insights |  | Bin Weight Integration (Prototype) | A dashboard component (initially simulated) to show garment bin weight vs. the target 90lb washer capacity. | Proves the value of optimizing washer capacity, which prevents variable quality and saves water/energy. |  | 1
Digital Twin & Operational Insights | Plant Floor Digital Twin | Health Trend Charting | Integrate a chart library (e.g., Recharts) to display historical trends in the Machine Detail Modal (DT-03). Must support views for the last 24 hours and 7 days of key metrics like temperature and vibration | Helps operators distinguish between a momentary glitch and a long-term degrading trend, leading to smarter maintenance decisions |  | 0.3
Digital Twin & Operational Insights | Plant Floor Digital Twin | Zone Summary Cards | A series of cards on the main dashboard that show aggregated KPIs for each factory zone. Required KPIs include: number of machines OK/Warning/Down, average uptime, and total open maintenance tickets | Provides a high-level KPI "roll-up" for managers and leadership to track overall zone performance without clicking each machine. |  | 0.5
Capital Asset Management (CAM) System | Asset Management & Capacity Forecasting | Asset Registry | Central system of record for all capital assets across all facilities, including model, serial, location, and status. | The foundational system that unifies all asset data (registry, condition, cost) from spreadsheets and tribal knowledge. |  | 0.2
Capital Asset Management (CAM) System | Asset Management & Capacity Forecasting | Downtime Tracking | Module to log and classify all downtime events (planned vs. unplanned, cause, duration). | Enables calculation of key metrics (MTBF, MTTR) to feed into degradation forecasts and stop "firefighting". |  | 0.6
Capital Asset Management (CAM) System | Holistic Preventative Maintenance Tracking System | Preventive Maintenance (PM) Plan | System to define, schedule, and track preventive maintenance tasks based on time or usage intervals. | Drives the crucial shift from reactive maintenance (high cost, high downtime) to proactive, planned maintenance. |  | 0.4
Capital Asset Management (CAM) System | Holistic Preventative Maintenance Tracking System | PM vs. Reactive Analysis | A dashboard visualizing the ratio of preventive vs. reactive maintenance work orders by asset, type, and facility. | A key KPI dashboard for leadership to measure the success of the CAM initiative and identify problem areas. |  | 0.2
Capital Asset Management (CAM) System | Holistic Preventative Maintenance Tracking System | Parts & Repair Cost Tracking | Ability to track the cost of parts and labor for every maintenance ticket, aggregated by asset. | Provides essential financial data needed to calculate the total cost of ownership (TCO). |  | 0.3
Capital Asset Management (CAM) System | Capital Deployment Optimization & Forecasting | Total Cost of Ownership (TCO) View | A summary view that combines all asset costs (capex, maintenance, downtime, energy) into a single TCO metric. | Answers the question, "How much is this machine really costing us?" to optimize capital. |  | 1
Capital Asset Management (CAM) System | Capital Deployment Optimization & Forecasting | Degradation Forecasting (Prototype) | A scoring model to forecast the remaining useful life of an asset based on age, downtime, and cost trends. | Answers "How much longer can it be used?" to enable proactive end-of-life decisions. |  | 1
Capital Asset Management (CAM) System | Capital Deployment Optimization & Forecasting | Replacement Priority Index | A single, calculated score that ranks all assets for replacement based on cost, life, downtime, and criticality. | Drives capex precision by ensuring capital is spent on the most critical, highest-risk assets first. |  | 1
Capital Asset Management (CAM) System | Capital Deployment Optimization & Forecasting | Capex Planning Dashboard | A leadership roll-up view of upcoming capital needs (based on the Replacement Index) by quarter and year. | The key strategic deliverable for finance/leadership to plan future capital needs based on data, not gut feel. |  | 1
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Unified Social Listening Feed | Develop strategy and targets for a single platform that aggregates all RtR mentions from Instagram, TikTok, Reddit, Trustpilot, etc.. and then returns a net promoter score and action tracking on content | Eliminates "blind spots" by capturing scattered feedback and detecting issues before they escalate. |  | 0.5
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Social Media Scrapping Strategy | System to programatically connect into target social media platforms (Facebook, X, Reddit, Instagram) and identify posts reference Rent the Runway. Posts to be extracted and saved into RtR database. | Provides a real-time "Brand Health" dashboard to monitor and close the -42.5 NPS gap. |  | 0.4
Customer Experience Digital Twin | Customer Sentiment Digital Twin | AI Customer Sentiment Analysis | An AI NLP will individually classify the content of each post and assign an NPS of 1 to 10. Sentiment to be charted and displayed on Customer Sentirment page. Auto-classifies posts into root-cause categories (e.g., fit, quality, stained, delivery, billing). | Transforms raw complaints into actionable operational insights, showing exactly what to fix first (e.g., delivery reliability, garment condition). |  | 0.4
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Customer Sentiment Analysis Dashboard | A dashboard delivering target metrics and KPIs from customer NPS. This dashboard will be a strong indicator of honest feedback from customers, and tracking quality escapes. Dashboard to breakdown the NPS score by social media platform and align a category of defect or success | The primary insight dashboard for leadership to track sentiment trends and the impact of operational fixes. |  | 0.2
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Emerging Issue Alerts | Automated alerts that detect spikes in specific negative categories (e.g., a sudden rise in "stained" or "late delivery" posts). | Enables a rapid response to systemic service failures, amplifying brand damage. |  | 0.2
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Action & Engagement Stub | A workflow tool allowing internal teams to mark a post as "responded," "refunded," or "escalated" for internal tracking. | Enables teams to act on feedback and tracks resolution to measure brand recovery and "save the day". |  | 0.3
Customer Experience Digital Twin | Customer Sentiment Digital Twin | Link-to-Ops (Prototype) | A feature to manually link a specific negative post to an internal entity (e.g., garment ID, machine, or batch). | The first step in creating a "Digital Twin of the Customer" by directly correlating a customer complaint to a specific operational failure. |  | 0.3
IoT Sensing | Soap Dosing Reliability | Solvent Dosing Reliability Coordination | Coordinate with RtR staff to evaluate IoT solutions to validate solvent delivery and purging to equipment. Opportunities exist to commercially negotiate sensing solution with chemical provider. ClearObject to assist in technology implementation and evaluation through the commercial and activation process. | Wet washing loads cannot measure solvent delivery (no solvent is delivered vs too much). Solution to validate solvent delivery to ensure wash cycle efficiency and mitigate garment damage |  | 1.4
| Quality Inspection Throughput | Operator Inspection Throughput | Capture performance of quality inspectors volume. Identify optimal practices and predict risky (lazy?) behavior by labelling of outliers and anomolies (increased volume, higher defect relation) |  |  | 0.7
| Conversational AI Performance Interrogator | Conversation AI Plant Investigator | With coordination and connection of data pipelines, IoT sensors, and operational data forming a digital thread of the factory, we have the ability to integrate a conversational AI to query plant performance, statistics, and other key attributes to inform decision making. This conversational AI will ingest fixed prompts and open text prompts to interrogate enterprise systems and deliver the necessary operational insights. |  |  | 1.6